## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | ADMIN | SB1/D1/T1 | check the validation of password
|  | SB1/D1/T2 | send the confirmation mail
|  | SB1/D1/T3 | send an email for changing the password
SB1/US2 | LENDOR | SB1/D2/T1 | Register Myself Using Gmail ID
|  | SB1/D2/T2 | Receive A Confirmation Mail
|  | SB1/D2/T3 | Login Into The System Using Gmail Id And Password
|  | SB1/D2/T4 | Modify The Account Password
|  | SB1/D2/T5 | retype password
|  | SB1/D2/T6 | forget password
|  | SB1/D2/T7 | verification mail for password
|  | SB1/D2/T8 | link to reset the password
|  | SB1/D2/T9 | reset the password
|  | SB1/D2/T10 | change the password
SB1/US3 | LENDEE | SB1/D3/T1 | send an email for changing the password
|  | SB1/D3/T2 | add the account details
|  | SB1/D3/T3 | edit the account details
|  | SB1/D3/T4 | Register Myself Using Gmail ID
|  | SB1/D3/T5 | Receive A Confirmation Mail
|  | SB1/D3/T6 | Login Into The System Using Gmail Id And Password
|  | SB1/D3/T7 | Modify The Account Password
|  | SB1/D3/T8 | retype password
|  | SB1/D3/T9 | forget password
|  | SB1/D3/T10 | verification mail for password
|  | SB1/D3/T11 | link to reset the password
|  | SB1/D3/T12 | reset the password
|  | SB1/D3/T13 | change the password

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
SB2/US1 | ADMIN |  | Enter the prohibited items
SB2/US2 | LENDOR |  | Add the item and its description
Add the location
add the account details
edit the account details
select the category of item to add
specify the caution money for item
select the added item
select the added item
Select the GuideLines
Select the Privacy Policy
Open prohibited items
SB2/US3 | LENDEE
Search the near by location
Search the item for rent
check the availability of item
Add the item into cart
view the cart
view the total amount
select the category for rent
select the item for wishlist
select the item from wishlist
Filter the item according to the price
Tap on the item
can sort the items
Filter the item according to the Size(Clothes,Shoes)
Filter item according to brand
Select the Notifications settings
Select the Help & support
Select the GuideLines
Open prohibited items
Select the Privacy Policy

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>
SB3/US1 | ADMIN |  | view the no of users
apply the opnion mining on review by customers
use dataset for recommendation system
implementation of algorithm for recommendation system
SB3/US2 | LENDOR |  | specify the discount offers
get the notification
return the caution money
can see the past activity
SB3/US3 | LENDEE |  | return the item
select the payment mode
get the notification
can see the past activity
Select the paytm mode for payment
Select the Credit/Debit card mode for payment

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Admin | check the validation of password | user's password strength is maintained | 1
1 | SB1/US2 | Admin | send the confirmation mail | user can get the confirmation mail | 1
1 | SB1/US3 | Admin | use dataset for recommendation system | recommendation system can be tested | 3
1 | SB1/US3 | Admin | implementation of algorithm for recommendation system | admin can recommend items to the user | 3
1 | SB1/US3 | Admin | view the no of users | I can analyse the increment or decrement of users | 3
|  | Admin | apply the opnion mining on review by customers | lendee can get highly rated product first | 3
|  | Admin | Enter the prohibited items | Lendor can not let it for rent | 2
|  | Admin | Testing of recommendation system algorithm | to increase the accuracy of recommendation system | 4
|  | Admin | Testing of whole system | to find the flaws of the system | 4
|  | Admin | Correcting flawdrawn out while testing | whole system can work accurately | 4
|  | Admin | Testing of opnion mining algorithm | to increase the accuracy of the opnion mining algorithm | 4
|  | Admin | send an email for changing the password | usercan change the password | 1
|  | Lendee | Add the location | I can search the near by location | 1
|  | Lendee | Search the near by location | I can search the near by lendors | 2
|  | Lendee | Search the item for rent | I can rent the appropriate item | 2
|  | Lendee | check the availability of item | I can rent the item in that duration | 2
|  | Lendee | Add the item into cart | I can keep a record of my item | 2
|  | Lendee | view the cart | I Can Keep A Check On My item | 2
|  | Lendee | add the account details | I can pay for item | 1
|  | Lendee | edit the account details | I can use my updated account | 1
|  | Lendee | view the total amount | I Can order the item | 2
|  | Lendee | pay the amount | I Can rent the item | 3
|  | Lendee | return the item | lendor can lend it to other user | 3
|  | Lendee | Fill the feedback form | I can rate the item | 4
|  | Lendee | Register Myself Using Gmail ID | I Can Receive A Confirmation/Verification Mail | 1
|  | Lendee | Receive A Confirmation Mail | I Can Access the account | 1
|  | Lendee | Login Into The System Using Gmail Id And Password | I Can View/Edit My Profile | 1
|  | Lendee | Modify The Account Password | I Can Keep My Account Secure | 1
|  | Lendee | retype password | to confirm the password | 1
|  | Lendee | forget password | I can change the password | 1
|  | Lendee | verification mail for password | I can get the link to reset the password | 1
|  | Lendee | link to reset the password | I can reset the password | 1
|  | Lendee | reset the password | I can login into account | 1
|  | Lendee | select the payment mode | I can pay for item | 3
|  | Lendee | select the category for rent | I can rent according to requirement | 2
|  | Lendee | select the item for wishlist | I can rent these items later | 2
|  | Lendee | select the item from wishlist | I can add it to cart | 2
|  | Lendee | change the password | I can secure my account | 1
|  | Lendee | get the notification | I can get the updates of the item | 3
|  | Lendee | Filter the item according to the price | I can get the suitable results | 2
|  | Lendee | Tap on the item | I can see the zoomed image of the item | 2
|  | Lendee | can see the past activity | I can keep check on my activity | 3
|  | Lendee | can sort the items | I can see the item according to price | 2
|  | Lendee | give feedback about website | admin can improve the website functionality and UI | 4
|  | Lendee | Filter the item according to the Size(Clothes,Shoes) | I can get best fitted item | 2
|  | Lendee | Filter item according to brand | I can get item according to my choice | 2
|  | Lendee | Select the paytm mode for payment | I can pay the amount via paytm | 3
|  | Lendee | Select the Credit/Debit card mode for payment | I can pay the amount via credit/debit card | 3
|  | Lendee | Select the Notifications settings | I can opt for push notifications to stay tuned to incredible deals | 2
|  | Lendee | Select the Help & support | I can get 24x7 help regarding payment and products | 2
|  | Lendee | Select the GuideLines | I can get to know how to use application | 2
|  | Lendee | Open prohibited items | I can view which items I can rent | 2
|  | Lendee | Select the Privacy Policy | I can get to know about terms and condition of using the application | 2
|  | Lendor | Add the item and its description | the lendee can viewthe item | 2
|  | Lendor | Add the location | lendee can search the near by location | 2
|  | Lendor | add the account details | I Can receive money | 2
|  | Lendor | edit the account details | I can use my updated account | 2
|  | Lendor | Register Myself Using Gmail ID | I Can Receive A Confirmation/Verification Mail | 1
|  | Lendor | Receive A Confirmation Mail | I Can Access the app | 1
|  | Lendor | Login Into The System Using Gmail Id And Password | I Can View/Edit My Profile | 1
|  | Lendor | Modify The Account Password | I Can Keep My Account Secure | 1
|  | Lendor | retype password | to confirm the password | 1
|  | Lendor | forget password | I can change the password | 1
|  | Lendor | verification mail for password | I can get the link to reset the password | 1
|  | Lendor | link to reset the password | I can reset the password | 1
|  | Lendor | reset the password | I can login into account | 1
|  | Lendor | select the category of item to add | lendee can search according to the category | 2
|  | Lendor | specify the caution money for item | I can have the assurity of item | 2
|  | Lendor | specify the discount offers | I can get more sales of item | 3
|  | Lendor | select the added item | I can delete the item | 2
|  | Lendor | select the added item | I can update the item | 2
|  | Lendor | Receive the feedback from lendee | I can improve my service | 4
|  | Lendor | change the password | I can secure my account | 1
|  | Lendor | get the notification | I can get the updates of the item | 3
|  | Lendor | return the caution money | lendee can get the money back | 3
|  | Lendor | can see the past activity | I can keep check on my activity | 3
|  | Lendor | give feedback about website | admin can improve the website functionality and UI | 4
|  | Lendor | Select the GuideLines | I can get to know how to use application | 2
|  | Lendor | Select the Privacy Policy | I can get to know about terms and condition of using the application | 2
|  | Lendor | Open prohibited items | I can view which items can be upload for rent | 2

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
SB4/US1 | ADMIN | SB4/D1/T1 | Testing of recommendation system algorithm
|  | SB4/D1/T2 | Testing of whole system
|  | SB4/D1/T3 | Testing of opnion mining algorithm
|  | SB4/D1/T3 | Correcting flawdrawn out while testing
SB4/US2 | LENDOR | SB4/D2/T1 | give feedback about website
|  | SB4/D2/T2 | Receive the feedback from lendee
SB4/US3 | LENDEE | SB4/D3/T1 | Fill the feedback form
|  | SB4/D3/T2 | give feedback about website

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days